## Sheet1
WBS entry | Task Description | Est'd hours | Assigned to | Priority
1 | Hawaii-1 to Hawaii-2RG installation preparation
1.1 | Mechanical installation of H2RG array mount | 40 | Solheid | Critical path
Detector, cables, BCS test array and final science array
1.2 | SDSU Gen III controller board modifications | 4 | Kulesa | Critical path
1.3 | SDSU DSP code development for H2RG on SDSU Gen III
| (1.3.1) Full array readout, 100 KHz, pixel resets | 40 | Kulesa | Critical path
| (1.3.2) Full array readout, 300 KHz, pixel and line resets | 16 | Kulesa | Medium
| (1.3.3) Dynamic loading of DSP code | 8 | Kulesa | High
| (1.3.4) "Windowed Mode", subarray operation | 60 | Kulesa | Low
1.4 | New "LiL" userspace library for H2RG array ops, deinterlacing, etc. | 20 | Kulesa | High
2 | Hawaii-1 to Hawaii-2RG Integration and Test
2.1 | Warm testing of expendable BCS array | 40 | Kulesa | Critical path
2.2 | Installation of Science grade array | 20 | Solheid | Critical path
2.3 | Initial Cold testing of Hawaii-2RG
| (2.3.1) Light sensitivity, clocking, biases, deinterlacing | 40 | Kulesa | Critical path
| (2.3.2) Array characterization: Read noise, gain, QE | 8 | Kulesa | Critical path
| (2.3.3) DSP optimization for observing (full frame) | 24 | Kulesa | Critical path
| (2.3.4) Characterization of observing modes (stray light, sensitivity, FoV) | 8 |  | Critical path
| (2.3.4.1) Imaging | 4 | Kulesa | Low
| (2.3.4.2) JHK long slit spectroscopy | 8 | Kulesa | High
| (2.3.4.3) LM long slit spectroscopy | 4 | Kulesa | Medium
| (2.3.4.4) Echelle spectroscopy, R=30,000 | 8 | Kulesa | Critical
| (2.3.4.5) Echelle spectroscopy, R=55,000 | 4 | Kulesa | Medium
2.4 | Integrate Gen III controller with ARIES server and GUIs
| (2.4.1) Upgrade GUI to current server | 8 | Kulesa | High
| (2.4.2) FPA plugin for H2RG selectable | 8 | Kulesa | High
| (2.4.3) Mac and Linux versions available for MMT/LBT/Bok | 16 | Kulesa | High
3 | Optomechanical & Operations tasks for ARIES
3.1 | Fix vacuum leak in LN2 fill flange (spectrometer) | 40 | Solheid | High
3.2 | Replace rubberized heaters for fill flanges with kapton heaters | 4
3.3 | "Two switch" heater control for fill manifold | 4
3.4 | Wire ortho-tilt motor on echelle grating via spare hermetic conductors | 16 | Kulesa
3.5 | Battery elimination circuit for both ARIES motor controllers | 8 | Kulesa | High
4 | Calibration Unit |  | Stone/Eisner w/ ARIES team
4.1 | Initial design |  |  | High
4.2 | Fabrication |  |  | High
4.3 | Lab integration & testing |  |  | High
4.4 | On sky testing |  |  | High
5 | Functionality upgrades |  | All
5.1 | Evaluate new slit fab technique (better throughput & in-house fab) |  |  | TBD
5.2 | Seeing limited slits (0.6-0.8" vs 0.2") |  |  | TBD
5.3 | Cross-dispersed low-resolution modes (simultaneous JHK and LM) |  |  | TBD
5.4 | Infrared tip/tilt sensing for AO secondary |  |  | TBD
5.5 | Atmospheric dispersion corrector characterization |  |  | TBD
6 | Documentation
6.1 | Refine observer's wiki |  | MMT and Kulesa
6.2 | Data processing collaboration effort |  | All
6.3 | Observation planning tools (echelle simulator, exposure time calculator) |  | MMT and Kulesa
SUMMARY
| Labor | total hours
| Solheid | 108
| Kulesa (all priorities) | 312
| Kulesa (critical path and high priority items only) | 244
| Purchasing items | $ USD
| Kapton heaters | 200
| Echelle motor actuator controller | 1100
| Calibration Unit | TBD
| New slits | TBD
| Cross-dispersion prism and new mount | TBD
| Vacuum refurbishment | TBD